## Risk Matrix
RISK MATRIX |  |  | LIKELIHOOD
|  |  | Rare | Unlikely | Possible | Likely | Almost Certain
|  | (description) | May only occour in | Could Occour in | Might occour at sometime | Will probably occure in most | Is expected to occur in most
CONSEQUENCE | Severe | Critical failure, preventing core activies from being perform | HIGH | VERY HIGH | VERY HIGH | EXTREME | EXTREME
| Major | Distrup key activities | HIGH | HIGH | VERY HIGH | VERY HIGH | EXTREME
| Moderate | Have impact to the organization | LOW | MEDIUM | MEDIUM | HIGH | VERY HIGH
| Minor | have some impact on business | VERY LOW | LOW | MEDIUM | MEDIUM | HIGH
| Insignificant | Minimal Impact on non-core | VERY LOW | VERY LOW | LOW | MEDIUM | MEDIUM

## Risk Assessment
Context - Asset(s) that we are trying to protect
The asset that need to be protected include: - Confidential Customer Data - Sensitive Data - Business & Financial Information - Intellectual Property - Infrastructure
Risk |  |  |  |  | Inherent Risk Rating |  |  | Current Risk Rating |  |  |  |  | Target Risk Rating
ID | Title | Description | Sources or Causes of Risk | Consequences of Risk | Likelihood | Consequence | Risk Level | Existing control measures | Effectiveness of exisitng control measures | Likelihood | Consequence | Risk Level | Additional control measures | Effectiveness of additional control measures | Likelihood | Consequence | Risk Level
R01 | Cyber Attack | an attack conduct by a group of people such as hacker, nation state actor, orgenaized crime groups, etc. it delibrate to gain unauthorized access to the organization assets or system or infrastructure. The goal is to steal sensitve or confidential information. | Nation state actors, organized crime groups, hackers. | Data loss, system downtime, reputational damage, financial loss | Likely | Major | VERY HIGH | Firewalls, Honeypots, IDS system, IPS system, anti-virus | Excellent / Good / Moderate / Weak - Firewalls: Excellent control. Configured, maintained, and tested properly. Highly effective to prevent threats. - IDS and IPS: Moderate control, configuration need to be improved. - Anti-virus: Excellent control. Effective and configuration has been set properly. | Possible | Major | VERY HIGH | Accept / Treat / Avoid / Transfer - Threat: Reduce the likelihood or impact of risk by: o Add Penetration testing o Regular Security Training - Transfer: Wen can transfer risk to 3rd party such as letting Managed Security Service Provider made the organization’s SIEM | Excellent / Good / Moderate / Weak - Penetrations Testing: Good control to simulate real cyber attack to test the organization system to identify vulnerability and weakness - SIEM: Excellent control. SIEM would enable real time monitoring of security events and generate alerts when detect any suspicious activity and help with incident response. | Unlikely | Moderate | MEDIUM
R02 | Natural Disaster | Unpredictable events that cause massive damage to the organization and people such as earthquake, flood, cyclone, brush fire or storm. | Natural phenomenon of nature | Financial loss, distruption of supply chains, property damage, loss of life | Rare | Severe | HIGH | Emergency response plan, backup power (such as generator) | Excellent / Good / Moderate / Weak - Emergency response plan: Good control. Can the organization has established emergency respond plan when natural disaster happened. - backup power (such as generator): Good control. The organization has configure backup power to support and ensure continuity of operation during natural disaster. | Rare | Moderate | LOW | Accept / Treat / Avoid / Transfer - Accept: Acknowledge the possibility of natural disaster happen - Transfer: Established or took an insurance from insurance company to cover potential financial loss if natural disaster happened | Excellent / Good / Moderate / Weak -Insurrance: Excellent control. Insurance is need to cover potential financial loss | Possible | Moderate | MEDIUM
R03 | Employee negligence or Human Error | Employee negligence arise when employe fail to follow established security protocol or polices or it can be employee action put the organization assets at risk. | Employee | Reputation, Confidential data or information, assets, financial loss | Possible | Moderate | MEDIUM | Security Awareness training | Excellent / Good / Moderate / Weak - Security Awareness training: Good control. The organization regularly conduct security awareness training for employee to prevent employee negligence or Human Error | Possible | Moderate | MEDIUM | Accept / Treat / Avoid / Transfer Threat: to reduce the impact of risk by doing: Monitoring and audit, incident response plan, Role-based access control. | Excellent / Good / Moderate / Weak Good:Regular testing and maintenance. Audit regularly and provide training when necessary. | Rare | Moderate | LOW
R04 | Ex-Employee stole cconfidential data | Former employee stole confidential data and published it / try to sell it / or try to blackmail the company and asking sum of money | Ambitions, Revenge | Secrets leak to competitor. | Possible | Major | VERY HIGH | implement strong access controls, immediately revoke access upon termination, encrypt sensitive data | Excellent / Good / Moderate / Weak - implement strong access controls: Excellent control. The organization has implemented strong access control to prevent unauthorized access. - immediately revoke access upon termination: Excellent control. The organization has implemented immediate revoke access to ex-employee to prevent unauthorized access. - encrypt sensitive data: Good control. The organization has encrypted all of sensitive data and assets so only authorized user has the access to encrypted data or assets. | Unlikely | Moderate | MEDIUM | Accept / Treat / Avoid / Transfer Treat: Reduce the likelihood by mandating identity access management. Transfer: Instruct the public relations team to take legal action against the former employees for stealing intellectual property. Advise the competitor to adhere to ethical business practices. | Excellent / Good / Moderate / Weak student to pick effectiveness and provide a description of any additional contol measures | Rare | Moderate | LOW
R05 | Un-authorized Access | someone gain access to restricted area or data or assets | non-authorized person, criminal, employee | Loss of finantial data, confidential information, and reputation damage | Possible | Major | VERY HIGH | RIFD, MFA, Surveillance Camera, Security Guard | Excellent / Good / Moderate / Weak - RIFD: Excellent control, the use of RIFD has been implemented in the organization - MFA: Good control, MFA has been implemented and configured across the organization - Surveillance Camera: Moderate control. Need to add more Surveillance camera. - Security Guard: Good control, security guard has been deployed to protect restricted place | Rare | Minor | VERY LOW | Accept / Treat / Avoid / Transfer Treat: role-based access, zero trust, monitoring, auditing, incident response plan | Excellent / Good / Moderate / Weak Excellent: Implement a zero-trust security model, enforce multi-factor authentication, establish a curfew for employees on the premises, and enforce strict access controls. | Rare | Insignificant | VERY LOW
Note on L6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective
Note on R6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective